## Work_Completion_Browse638857704
Work Completion Browse
Project : LE PARADIS
Contractor : TOHARUN (Bokul )
From Date : 17/05/2002 To date: 17/05/2002
Page 1 of 1
Total Records: 27 Records 1 to 27
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE First Floor - Flooring | 7.47 | 204.5 | 0 | 1527.615 | 0 | 2024-11-08 15:13 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Service Fourth Floor -Wall dado | 6.02 | 204.5 | 0 | 1231.09 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Balcony Fifth Floor - Flooring | 9.34 | 204.5 | 0 | 1910.03 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Balcony Fourth Floor -Flooring | 11.24 | 204.5 | 0 | 2298.58 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Fifth Floor - Flooring | 2.17 | 204.5 | 0 | 443.765 | 0 | 2024-11-08 15:13 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Third Floor - Flooring | 19.01 | 204.5 | 0 | 3887.545 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Service Fifth Floor - Flooring | 3.92 | 204.5 | 0 | 801.64 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Service Fourth Floor -Flooring | 1.96 | 204.5 | 0 | 400.82 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
CERAMIC TILES LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Service Fifth Floor - Wall dado | 11.64 | 204.5 | 0 | 2380.38 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR FLOOR TILE (600 MM X 600 MM) | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A CORE First Floor - Corridor floor | 10.6 | 236.5 | 0 | 2506.9 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR FLOOR TILE (600 MM X 600 MM) | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A CORE Fifth Floor - Corridor floor | 43.72 | 236.5 | 0 | 10339.78 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR FLOOR TILE (600 MM X 600 MM) | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A CORE Fourth floor - Corridor floor | 43.72 | 236.5 | 0 | 10339.78 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Corridor Fourth floor -Skirting | 53.04 | 36 | 0 | 1909.44 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Corridor First Floor - Skirting | 12.39 | 36 | 0 | 446.04 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE First Floor - Skirting | 69.3 | 36 | 0 | 2494.8 | 0 | 2024-11-08 15:13 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Third Floor -Skirting | 142.51 | 36 | 0 | 5130.36 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Balcony Fifth Floor -Skirting | 18.6 | 36 | 0 | 669.6 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Balcony Fourth floor -Skirting | 22.38 | 36 | 0 | 805.68 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR VITRIFIED SKIRTING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Corridor Fifth Floor -Skirting | 53.04 | 36 | 0 | 1909.44 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR WALL DADO LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Toilet Fourth Floor - Wall Dado | 24.48 | 204.5 | 0 | 5006.16 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR WALL DADO LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Toilet First Floor - Wall Dado | 38.91 | 204.5 | 0 | 7957.095 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR WALL DADO LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Kitchen & Wash basin Fifth Floor - Wall Dado | 13.52 | 204.5 | 0 | 2764.84 | 0 | 2024-11-08 15:13 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR WALL DADO LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Kitchen & Wash basin Fourth Floor - Wall Dado | 11.6 | 204.5 | 0 | 2372.2 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR WALL DADO LAYING | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Kitchen & Wash basin Third Floor - Wall Dado | 4.34 | 204.5 | 0 | 887.53 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
Labour charges for floor tile(1200mm x 600mm) | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE First Floor - Flooring | 85 | 236.5 | 0 | 20102.5 | 0 | 2024-11-08 15:13 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
Labour charges for floor tile(1200mm x 600mm) | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Third Floor - Flooring | 159.33 | 236.5 | 0 | 37681.545 | 0 | 2024-11-08 15:01 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )
L/C FOR TERRACE TILE | N/C | N/C | TOHARUN (Bokul ) | 135 | 2024-08-27 | A - CORE Terrace Tile Laying Work | 369.1229 | 204.5 | 0 | 75485.6331 | 0 | 2024-11-08 14:44 | As Per completion | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | TOHARUN (Bokul )