## Project_Work_Order6388586331669
Project Work Order
From 19 May 2002 To 19 Jun 2025
Page 1 of 1
Total Records: 14 Records 1 To 14
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for Soap wash clean work | SQM | 441.92 | 10.76 | 4755.06 | 0 | 4755.06 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for Soap wash clean work | SQM | 441.92 | 10.76 | 4755.06 | 0 | 4755.06 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for Soap wash clean work | SQM | 70.98 | 10.76 | 763.74 | 0 | 763.74 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for Soap wash clean work | SQM | 70.98 | 10.76 | 763.74 | 0 | 763.74 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for application of Cement grout | SQM | 441.92 | 32.29 | 14269.6 | 0 | 14269.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for application of Cement grout | SQM | 441.92 | 32.29 | 14269.6 | 0 | 14269.6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-WALL BLOCK H-1ST FLOOR | Labour charges for application of Cement grout | SQM | 343.3 | 32.29 | 11085.16 | 0 | 11085.16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 343.3 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-WALL BLOCK H-2ND FLOOR | Labour charges for application of Cement grout | SQM | 343.3 | 32.29 | 11085.16 | 0 | 11085.16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 343.3 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for application of Epoxy grout | SQM | 70.98 | 64.58 | 4583.89 | 0 | 4583.89 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for application of Epoxy grout | SQM | 70.98 | 64.58 | 4583.89 | 0 | 4583.89 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for laying of protection sheet | SQM | 441.92 | 10.76 | 4755.06 | 0 | 4755.06 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | CEMENT GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for laying of protection sheet | SQM | 441.92 | 10.76 | 4755.06 | 0 | 4755.06 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 441.92 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-1ST FLOOR | Labour charges for laying of protection sheet | SQM | 70.98 | 10.76 | 763.74 | 0 | 763.74 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0
LE PARADIS | 221 | 0 | 07 Jun 2025 | MUTHUKUMAR A | EPOXY GROUT-FLOOR BLOCK H-2ND FLOOR | Labour charges for laying of protection sheet | SQM | 70.98 | 10.76 | 763.74 | 0 | 763.74 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 70.98 | 0 |  |  | Priyank | Manoj | Priyank | construction |  |  | FLOORING WORK | Approved | Priyank |  | 0